## Slide 1: H->bb Weekly Meeting
Ricardo Gonçalo (RHUL)
HSG5 H->bb Weekly Meeting, 11 April 2011

## Slide 2: Apologies…
I have completely dropped the ball over the past week due to on-call shift duties…
Had no chance of doing anything that involved thinking, like setting up a task list or looking at the MC samples… sorry!

## Slide 3: News! News! News!
Meeting last week:
Simulation workshop tomorrow aimed at the physics needs for 2011-2012 data analysis: https://indico.cern.ch/conferenceDisplay.py?confId=133590
Forthcoming meetings:
LHC Physics Center (LPCC): Status of Higgs and BSM searches at the LHC – starting TODAY at 2pm and tomorrow https://indico.cern.ch/conferenceDisplay.py?confId=127277
New meeting on procedures for statistical interpretation of ATLAS results on April 15: https://indico.cern.ch/conferenceDisplay.py?confId=132499
Workshop on combined performance for 2011, on 14 April: https://indico.cern.ch/conferenceDisplay.py?confId=132123

## Slide 4: Monte Carlo Samples
From last week:
  Need to review what we have and what we need for the coming year:
  Several ongoing strands:
    Giacinto looking into Wbb in Powheg
    Michiel looking into MC@NLO for VH signal
    Michiel/Chris C-T, Aurelio: discussion of ttbb ME production in Alpgen
    Mass points:
    ZH(Zll), WH(Wlnu), ttH, VBF(Hbb) analyses have mass points: 115, 120, 125, 130 GeV/c2
  Any more WH/ZH (boosted/non-boosted) samples needed?
  Additional backgrounds?
Michiel giving a talk today
We urgently need to check the available MC samples
  The HSG5 request for this summer was already sent (see email from Chris C-T on Thursday 7/4)

## Slide 5: Task Assignment
Need to study systematic effects and try to improve on them
Effects should be evaluated with at least 1fb-1 in mind
  What is the effect of each systematic uncertainty or each alternative reconstruction method on S/√B
In addition need someone to:
  Follow developments of MC/D3PD production
  Follow up on trigger evolution – in touch with Higgs trigger group
  Follow up on GRL issues

## Slide 6
Task | Obs | Candidate(s)
Trigger: study optimal trigger for the 2011 data Bear in mind that single-lepton triggers will likely increase to pT thresholds of ≈20 GeV – i.e. analysis cuts will need to increase to ≈22 GeV; check also any sculpting, angular acceptance, etc | Does this need AODs? Enough info on WZ/top D3PDs? Sample A or sample T should have the foreseen menus Liaise with Gemma Wooden | 
Muon reconstruction: investigate different options |  | 
Electron reconstruction: investigate alternatives | Inclusion/exclusion of cracks Inner detector cuts (B layer?) | 
Pileup: what do we need to do with 2011 pileup | Reweighting method Jet vertex fraction Choice of vertex reconstruction | 

## Slide 7
Task | Obs | Candidate(s)
Jet energy scale: investigate size of systematic uncertainty | Worry about b jets Any way to improve di-jet mass resolution? Liaise with JetETmiss | 
B tagging algorithms | Effect of each different choice on significance | 
Fast monitoring: implement WH baseline selection in online monitoring infrastructure | Example exists Involves programming in Athena Liaise with Fabien Tarrade | 
Lots of other things… |  | 

## Slide 8: AOB
Are we happy with the schedule of meetings?
  Sau Lan proposes 13:00 or 13:30 on Mondays
  Would that be ok for everyone? Any other preferences?

## Slide 9: Backup

## Slide 11
Date | Milestones wish list
17 May | Dubna workshop – analysis frozen After this: add data to un-boosted analysis and prepare for result approval Concentrate more effort on boosted VH with a view to obtaining results quickly
10 May | Review results with 2011 data from cut-based and multivariate analyses
3 May | Margin for dealing with unforeseen problems
26 April | Start looking at 2011 data if enough is available. Any surprises? How does the MC describe the new data? By now we should have a reasonable idea of results from the multivariate analysis
19 April | End of 2 weeks of beam scrubbing. (I’m away for Easter)
12 April | By now we should have a reasonable idea of the exclusion of the cut-based analysis First report on MVA preliminary results – establish plan for getting results by Dubna
5 April | Identify the worst systematics and discuss any possible improvements: Any changes needed in analysis cuts? Any study necessary for corrections to some systematic effect? Multivariate analysis: iterate on preselection cuts, methods, questions Assign tasks – divide the work to achieve better results!
29 March | Establish analysis cuts: If possible as result of optimization Use 2010 data to develop cuts and show that data is well described by background MC Start evaluating systematics
22 March | Iterate on analysis cuts – why is each cut applied at each particular value? Start iteration on multivariate methods to improve analysis

## Slide 12: Reconstruction issues
Muon CP group recommendations for release 16:
  Reconstruction efficiency and isolation efficiency scale factors, momentum smearing functions
  https://twiki.cern.ch/twiki/bin/view/AtlasProtected/MCPAnalysisGuidelinesRel16
Jet/Etmiss recommendations for jet cleaning in release 16:
  Medium jet cleaning should give similar rejection to rel 15 cleaning but with better efficiency
  Tight jet cleaning should not be used – still under discussion
  https://twiki.cern.ch/twiki/bin/view/AtlasProtected/HowToCleanJets#Bad_jets_rel16_data
New!: Final b-tagging calibrations for release 16 based on full 2010 data:
  https://twiki.cern.ch/twiki/bin/view/AtlasProtected/Analysis16
e/gamma recommendations for energy scale and resolution in release 16:
  https://twiki.cern.ch/twiki/bin/view/AtlasProtected/EnergyScaleResolutionRecommendations
  And rescaler tool: https://twiki.cern.ch/twiki/bin/view/AtlasProtected/EnergyRescaler
Standard Model W/Z group baseline selection for release 16 (next 4 slides):
  See discussion in W/Z group Sharepoint
  Also, finer points (and perhaps the not so fine) still being discussed