## Slide 1: H->bb Note Schedule
Ricardo Gonçalo (RHUL)
HSG5 H->bb WH/ZH note meeting with Editorial Board, 28 June 2011

## Slide 2: Last call for EPS
June 23rd: final “analysis update”
  Assumes ~ 7-10 days to run full analysis
  Data taken up to June 18th available with GRL (recorded L=1 fb-1);
Jul 5th: Drafts submitted to EdBoard
  Early drafts should be circulated to the EdBoard earlier; very similar to PLHC
  Final drafts on Jul 8th to PC;
Jul 9th: last circulation of Papers/Notes
    Run again the full analysis to include the data after June 26th , at least for benchmark analyses? (technical stop on June 29thth, for ~10 days)
Jul 15th: last approval meetings
  Present the circulated results and the ones obtained updating the analysis
Jul 18th: conclude sign-offs of Papers/CONF Notes
  Assumes 1 week for EdBoard and two sign-offs from PC/PubComm/Mngt
  1820: 3 days contingency
Jul 21st: EPS Conference
Leandro (ATLAS Week)

## Slide 3: Statistics issues
All ATLAS results for summer conferences should be made using CLs
(All except analyses with a Bayesian history and Bayesian usage in CMS)

## Slide 4: Need to discuss…
INT note approval – what’s missing?
  Systematics: b-tagging, JES
  Limits: status…
  Anything else?
Life after INT – need to plan meetings for CONF editorial board approval – will everyone be available?

## Slide 5: Potentially relevant…
Some development on the boosted VH side
Boosted H->bb not included in note so far!
Hint of W->jj peak hints at sensitivity for Higgs with more data – paves way for future results
Shown at H->bb meeting today
Discussion started with Phys.coord. about possibly how to make these public

## Slide 6: Backup

## Slide 7: WH/ZH Note: Missing Ingredients
Moving to MC10b: done
b tagging:
  Need advanced tagger for increased background rejection
  Efficiency scale factors almost done
  Calibration & fake rate: preliminary on week of 20th June - will re-do analysis with final numbers
  IP3D+SV1, 60% efficiency working point
Jet Vertex Fraction:
  Fix exists but applicable only to AOD-based analyses – i.e. only one analysis in our group
  D3PDs including the bug fix exist for part of the 2011 run – being transferred to Grid site
  Validation?
Editorial board:
  Richard Bateley (chair)
  Alex Read
  Emmanuel Lemonier
  Niels van Eldik
    Good 1st meeting with Ed.Board
QCD background (incl. bb, cc):
  Almost there
  One feature to be understood in anti-track isolation QCD background in electron channel
  Watch this space!
Systematics:
  First estimates done – dominated by b-tagging uncertainty (around 30%)
SM Higgs combination:
  Need to produce inputs for SM Higgs combination